## PSEA WG Nepal
Output | Activity number | Activity | 2021 |  |  |  | 2022 | Responsible agency | Remarks/Status
|  |  | Q1 | Q2 | Q3 | Q4
Output 1: Increased Accountability, Governance, Management and Coordination among stakeholders at various levels | 1.1 | Ensure smooth running of PSEA WG | [5 empty] | PSEA WG co-chairs
| 1.1.1 | Update list of Agency PSEA Focal Points | [5 empty] | PSEA WG co-chairs | Moved to Q2
| 1.1.2 | Finalise Integrated ToRs and organise dedicated Working Group meeting on roles and responsibilities | [5 empty] | PSEA WG co-chairs | Moved to Q2
| 1.1.3 | Send letter signed by RC requesting HoA to include PSEA-related functions into performance evaluations of all PSEA Focal Points | [5 empty] | PSEA WG co-chairs | Moved to Q2/Q3
| 1.2 | Continue to provide regular updates through UNCT and PSEA Working Group meeting | [5 empty] | PSEA Coordinator with PSEA WG co-chairs
| 1.3 | Finalise one-pager on recommended agency-level actions to strengthen SEA/SH measures | [5 empty] | PSEA Coordinator with PSEA WG co-chairs
| 1.4 | Organise dialogue between UN and key humanitarian and development partners. | [5 empty] | PSEA Coordinator with PSEA WG co-chairs | Timeline TBC
| 1.5 | Knowledge and experience exchange across Asia-Pacific region (Bi-monthly PSEA Asia Pacific Brownbags) | [5 empty] | PSEA Coordinator with PSEA WG co-chairs
| 1.6 | Implement the OMT-HR Task Force and PSEA Working Group action plan on safeguards in hiring UN personnel and implementing partners | [5 empty] | PSEA Coordinator with PSEA WG co-chairs and OMT
| 1.7 | Establish PSEA information and reporting mechanisms as part of the COVID-19 vaccine roll-out. | [5 empty] | PSEA Coordinator with PSEA WG co-chairs with WHO/Health Cluster
| 1.7.1 | Identify PSEA focal points within health structures | [5 empty] | PSEA Coordinator with PSEA WG co-chairs with WHO/Health Cluster | Timeline TBC
| 1.7.2 | Inform health staff about the role of PSEA focal points | [5 empty] | PSEA Coordinator with PSEA WG co-chairs with WHO/Health Cluster
| 1.8 | Establish and ensure smooth running of CSO PSEA Network | [5 empty] | PSEA WG co-chairs with GiHA WG
| 1.8.1 | Develop ToR | [5 empty] | PSEA WG co-chairs with GiHA WG | Moved to Q2/Q3
| 1.9 | Support GTG and IDPG GESI on efforts on Sexual Harassment, including on leadership dialogues and creating a speak-up culture
| 1.1 | Establish engagement with Government | [5 empty] | PSEA WG co-chairs
| 1.11 | Submit End of Year Management Letter | [5 empty] | PSEA WG co-chairs
| 1.12 | Carry out risk assessment | [5 empty] | PSEA Coordinator with PSEA WG co-chairs | Moved to Q2/Q3/Q4
Output 2: Effective, comprehensive and inclusive mechanisms to ensure greater awareness on SEA/SH at all levels, including through addressing culture | 2.1 | Draft letter reminding of PSEA obligations with Standard of Conduct based on the SG’s Bulletin on SEA and SH with dissemination to all staff and other personnel regardless of contract modalities. | [5 empty] | PSEA WG co-chairs
| 2.2 | Conduct dedicated all staff Townhall on PSEA. | [5 empty] | PSEA WG co-chairs
| 2.3 | Roll out revised UNDSS Security Briefing for induction of all new personnel (through rotational facilitation by PSEA Focal Points) | [5 empty] | PSEA WG co-chairs with UNDSS and PSEA Focal Points
| 2.4 | Prepare standard PSEA Presentation for PSEA Focal Points to conduct sessions in their respective agencies. Presentations will be contextualised by focal points to indicate relevant reporting mechanisms | [5 empty] | PSEA WG co-chairs | Moved to Q2/Q3
| 2.5 | Develop materials to ensure clear messaging on PSEA across all UN field presences. | [5 empty] | PSEA WG co-chairs
| 2.6 | Develop and disseminate clear and consistent messages on PSEA that are accessible and context specific. | [5 empty] | PSEA WG co-chairs with RCCE
Output 3: Ensure victim-centred, confidential, effective and localised complaints/investigations mechanisms and support services are in place for all victims/survivors of SEA/SH. | 3.1 | Finalise UN Nepal Mechanism to Handle SEA reports including flowchart on roles and responsibilities upon reporting and Standard Operating Procedures | [5 empty] | PSEA WG co-chairs | Moved to Q2/Q3
| 3.1.1 | Assessment of UN support services (short, medium and long term) available for victims/survivors in Nepal, including through OIOS | [5 empty] | PSEA WG co-chairs / PSEA Coordinator | Moved to Q2/Q3
| 3.1.2 | Assessment of potential saftey and security risks of victims/survivors of SEA in Nepal, including reprisals, and development of guidelines on how to mitigate them
| 3.1.3 | Develop referral pathway for services jointly across Nepal | [5 empty] | PSEA WG co-chairs with Protection Cluster and GBV Sub-cluster | Moved to Q2/Q3
| 3.2 | Establish a hotline through the UNDSS Radio Room | [5 empty] | PSEA WG co-chairs | Continuing in Q2/Q3
| 3.2.1 | Revision of the e-SRM | [5 empty] | PSEA WG co-chairs | Activity deleted
| 3.2.2 | Training of trainers | [5 empty] | Hired NGO | Timeline TBC
| 3.2.3 | Training (including on first response to violence) provided by GBV Sub-cluster to ensure a victim/survivor-centric and rights-based approach | [5 empty] | PSEA WG co-chairs | Timeline TBC
| 3.3 | Organise training to PSEA Focal Points | [5 empty] | PSEA WG co-chairs | Timeline TBC
| 3.4 | Establish linkages between UNDSS Radio Room and other GBV hotlines | [5 empty] | PSEA WG co-chairs with GBV cluster
| 3.4.1 | Guidelines to guide survivors to report cases involving UN/ aid workers.
| 3.4.2 | Develop pathways for existing national GBV service providers and hotlines to report cases of SEA to UNDSS Radio Room (with consent of victim/survivor)
| 3.5 | UNCT approach of Focal Point for Victims' Rights | [5 empty] | PSEA WG co-chairs | Appointment completed
| 3.6 | Explore possibility of making PEP kits available for victims/survivors of SEA | [5 empty] | PSEA WG co-chairs and UNDSS | Timeline TBC