## PSEA Working Group workplan-202
Output | Activity number | Activity | 2021 |  |  |  | 2022 |  | Responsible agency | Remarks
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Outcome 1: PSEA inter-agency country-level structure The Resident Coordinator and UNCT/HCT are supported at senior management and technical-levels to lead, oversee, and deliver on the above four PSEA Outcomes. | 1.1 | Ensure smooth running of PSEA WG | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2021 Q1 to 2021 Q3; 2022 Q1 to 2022 Q2
| 1.1.1 | Update list of Agency PSEA Focal Points | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2021 Q1; 2022 Q1
| 1.1.2 | Finalise Integrated TOR, which incorporates roles and responsibilities of the RC, PSEA WG Co-chairs, VRA, PSEA WG, PSEA Coordinator, and PSEA Focal Points | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2021 Q3
| 1.1.3 | Present finalized TOR to the WG and UNCT | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2021 Q3
| 1.1.4 | RC to send letter to HoAs requesting the inclusion of PSEA related functions and responsibilities in performance evaluations of PSEA Focal Points | [6 empty] | PSEA Coordinator with PSEA WG co-chairs
| 1.2 | Finalise one-pager on recommended agency-level actions on SEA/SH and disseminate to all Agencies | [6 empty] | PSEA Coordinator with PSEA WG co-chairs
| 1.3 | Organise Annual Extraordinary UNCT Meeting on PSEA | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2021 Q2; 2022 Q2
| 1.4 | Explore opportunities for engagement with the Government on PSEA | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2022 Q1 to 2022 Q2
| 1.5 | Establish PSEA CSO Network | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and GIHA WG | bar: 2022 Q1 to 2022 Q2
| 1.6 | Carry out PSEA risk assessment | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2022 Q1 to 2022 Q2
| 1.7 | Continue the facilitation of a community of practice across the Asia-Pacific Region through quarterly Brownbags (in collaboration with DCO) | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and DCO Asia Pacific | bar: 2021 Q1 to 2021 Q3; 2022 Q1 to 2022 Q2
| 1.8 | In collaboration with the GTG and IDPG identify collective initiatives on addressing sexual harassment including leadership dialogues | [6 empty] | PSEA Coordinator with GESI and GTG | bar: 2022 Q1 to 2022 Q2
| 1.9 | Submit End of Year Management Letter | [6 empty] | RC with support from PSEA Coordinator and co-chair
Outcome 2: Prevention All United Nations staff and related personnel know the UN standards of conduct for protection from sexual exploitation and abuse and understand their personal and managerial responsibilities to address sexual exploitation and abuse and other misconduct. | 2.1 | Send letter to all staff/personnel reiterating our obligations on PSEA based on SG’s Bulletin on SEA and SH | [6 empty] | RC with support from PSEA Coordinator and co-chair | bar: 2021 Q1; 2022 Q1
| 2.2 | Implement the OMT-HR Task Force and PSEA WG joint actions on safeguards for hiring UN Personnel and Implementing partners. | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and OMT | bar: 2021 Q3; 2022 Q1 to 2022 Q2
| 2.2.1 | Roll-out revised UNDSS Security Briefing for induction of all UN Personnel (rotational basis by PSEA Focal Points) | [6 empty] | PSEA Coordinator WG co-chairs with UNDSS and PSEA Focal Points | bar: 2021 Q1 to 2021 Q3; 2022 Q1 to 2022 Q2
| 2.2.2 | Prepare and disseminate standard PSEA Presentation for PSEA Focal Points to conduct sessions for all staff (presentations contextualized for each agency by focal points) | [6 empty] | PSEA Coordinator with OMT, PSEA WG co-chairs and PSEA Focal Points | bar: 2021 Q3
| 2.2.3 | Conduct dedicated all staff townhall on PSEA | [6 empty] | PSEA Coordinator with PSEA WG co-chairs | bar: 2021 Q3; 2022 Q2
| 2.3 | Develop common communication materials to ensure clear messaging on PSEA across all UN field presences. | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and UNICEF | bar: 2021 Q3
| 2.4 | Ensure PSEA in health Structure | [6 empty] | PSEA Coordinator with Health Cluster | bar: 2021 Q3; 2022 Q1 to 2022 Q2
| 2.4.1 | Incorporate PSEA into the National Strategic Action Plan for Protection Cluster | [6 empty] | PSEA Coordinator with Protection Cluster and PSEA WG co-chairs | bar: 2021 Q3
| 2.4.2 | Carry out PSEA Orientation to all cluster co-leads | [6 empty] | PSEA Coordinator with Health Cluster co-leads (UNFPA, WHO) | bar: 2022 Q1
| 2.4.3 | Initiate discussion with Health Cluster co-leads on the integration of PSEA Session into existing training packages on COVID-19 response | [6 empty] | PSEA Coordinator with Health Cluster co-leads (UNFPA, WHO)
| 2.4.4 | In collaboration with Health Cluster co-leads and Government counterparts, develop and disseminate PSEA IEC Materials targeting health personnel | [6 empty] | PSEA Coordinator with UNICEF and Health Cluster co-leads (UNFPA, WHO) and support from PSEA co-chairs | bar: 2021 Q3
Outcome 3: Safe and accessible reporting Every child and adult recipient of United Nations assistance has access to a safe, gender and child-sensitive pathways to report sexual exploitation and abuse (including through community-based complaints mechanisms) that lead to assistance, are appropriate to the context and accessible to those in the most vulnerable situations). | 3.1 | Finalise the establishment of a gender and child-sensitive UN Nepal Mechanism for handling SEA reports (including flowchart and SOP) | [6 empty] | PSEA Coordinator with PSEA WG co-chairs with support from GBV and Protection Cluster | bar: 2021 Q1 to 2021 Q3
| 3.2 | Establish a hotline through the UNDSS Radio Room | [6 empty] | PSEA Coordinator with PSEA WG co-chairs with support from GBV and Protection Cluster | bar: 2021 Q2 to 2021 Q3
| 3.2.1 | Carry out first responded training to radio room operators to ensure a victim/survivor centred, child sensitive and rights based approach | [6 empty] | PSEA Coordinator with PSEA WG co-chairs with support from GBV and Protection Cluster
| 3.2.3 | Establish linkages between UNDSS Radio Room and other GBV and CP hotlines to identify and report SEA cases linked to UN | [6 empty] | PSEA Coordinator with PSEA WG co-chairs with support from GBV and Protection Cluster | bar: 2022 Q1 to 2022 Q2
| 3.2.3 | Develop guidelines for GBV and CP hotlines to guide victims to report cases involving the UN and refer cases to UNDSS Radio Room | [6 empty] | PSEA Coordinator with PSEA WG co-chairs with support from GBV and Protection Cluster | bar: 2022 Q1 to 2022 Q2
| 3.3 | Carry out training to PSEA Focal points on the reporting mechanisms and procedures | [6 empty] | PSEA Coordinator with PSEA WG co-chairs with support from GBV and Protection Cluster | bar: 2022 Q1 to 2022 Q2
| 3.4 | Develop and disseminate clear and consistent messages on PSEA that are accessible and context specific (including in local languages) | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and UNICEF | bar: 2022 Q1 to 2022 Q2
Outcome 4: Victims’ right to assistance Every child and adult victim/survivor/complainant is offered immediate, quality assistance (medical care, psychosocial support, legal assistance, reintegration support). | 4.1 | Strengthen common provision of victim assistance | [6 empty] | PSEA Coordinator with Victim's Right Focal Point, Protection Cluster and GBV sub-cluster | bar: 2021 Q1 to 2021 Q3; 2022 Q1 to 2022 Q2
| 4.1.1 | Map existing support services available for victims/survivors across Nepal | [6 empty] | PSEA Coordinator with Victim's Right Focal Point, Protection Cluster and GBV sub-cluster | bar: 2021 Q3
| 4.1.2 | Develop referral pathway SOP integrating GBV and CP services | [6 empty] | PSEA Coordinator with Victim's Right Focal Point, Protection Cluster and GBV sub-cluster | bar: 2021 Q3
| 4.1.3 | Develop guidance for agencies to integrate assistance into programme development | [6 empty] | PSEA Coordinator with Victim's Right Focal Point, Protection Cluster and GBV sub-cluster | bar: 2022 Q1
| 4.2 | Establish pooled UNCT funds for victim assistance | [6 empty] | PSEA Coordinator with Victims Rights' Focal Point and PSEA co-chairs
Outcome 5: Accountability and investigations Every child and adult victim/survivor of sexual exploitation and abuse who is willing has their case investigated in a prompt, and safe way in accordance with a victims’/survivors’ rights approach. | 5.1 | Develop and roll-out common Implementing Partner Capacity Assessment Tool (based on IASC and UNICEF guidelines) | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and UNCT | Supporting outcomes 4 as well | bar: 2022 Q1 to 2022 Q2
| 5.2 | Implement the OMT-HR Task Force and PSEA Working Group action plan on safeguards in hiring UN personnel and implementing partners | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and OMT | Same as 2.2 | bar: 2021 Q1 to 2021 Q3; 2022 Q1 to 2022 Q2
| 5.3 | Roll out a pilot training to support capacities of implementing partners to respond to SEA allegations, including on victim-centred provision of assistance and investigation | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and UNICEF | The implementing partners will be selected among those already assessed in their overall PSEA capacities, in particular UNICEF partners | bar: 2022 Q1
| 5.3.1 | Conduct capacity mapping of implementing partners on provision of assistance and investigations | [6 empty] | PSEA Coordinator with PSEA WG co-chairs and UNICEF | The implementing partners will be selected among those already assessed in their overall PSEA capacities, in particular UNICEF partners | bar: 2022 Q1
| 5.3.2 | Develop common training package on victim-centred response to implementing partner focal persons in charge of investigation procedures | [6 empty] | PSEA Coordinator with Victims Rights' Focal Point, GBV sub-cluster and PSEA co-chairs | bar: 2022 Q1 to 2022 Q2