## Network
GAZIANTEP CROSS BORDER
INTER-AGENCY PSEA NETWORK- WORK PLAN JANUARY 2018-DECEMBER 2018
OVERALL OBJECTIVE
To reduce the prevalence of Sexual Exploitation and Abuse in Northern Syria
Intended outputs | Timeframe | [11 empty] | Indicative Activities | Inputs/actors responsible
| J | F | M | A | M | J | J | A | S | O | N | D
ENGAGEMENT WITH AND SUPPORT TO PARTNERS AND LOCAL COMMUNITIES
Objective: Increase engagement and support with actors on PSEA | [12 empty] | 1. Package information/contextualizing it to the Syria context | DRHC's office, PSEA Coordinator, Participating Organizations and their partners, HLG, PSEA Network, PSEA/CBCM focal persons, affected communities, donors. | bar: Timeframe M to Timeframe A; Timeframe S to Timeframe O
2. Translate awareness materials in relevant languages (Arabic, English, Turkish, Kurdish) such as - leaflets, banners, posters, etc. | bar: Timeframe A to Timeframe M; Timeframe O to Timeframe N
3. Organize orientation for all staff of humanitarian Organizations. | bar: Timeframe M to Timeframe D
4. Undertake awareness raising for communties, humanitarian workers and other key actors. | bar: Timeframe M to Timeframe D
5.Facilitate signing of PSEA code of conduct and statement of commitment on elimination of SEA by actors. | bar: Timeframe M to Timeframe D
6. Conduct Focus Group Discussions with frontliners and communities in Syria on SEA using Age, Gender and Diversity approach. | bar: Timeframe A to Timeframe J; Timeframe O to Timeframe D
7.Engage UN implementing partners, beneficiaries of humanitarian fund and PSEA network members to mainstream PSEA in their regular programming. | bar: Timeframe F to Timeframe D
8. Undertake strategic engagement with donors on PSEA. | bar: Timeframe M to Timeframe D
9. Organize targeted and strategic meetings with different partners to engage and lobby their support to prevent and respond to sexual exploitation and abuse. | bar: Timeframe M to Timeframe D
10. Conduct mapping of Organizations with operation in Northern Syria for effective involvement and collaboration/inform programming on PSEA activities. | bar: Timeframe F to Timeframe D
11. Undertake stakeholders analysis to understand community structures for appropriate engagement on PSEA | bar: Timeframe M to Timeframe D
12. Coordinate with stakeholders inside Syria on PSEA. | bar: Timeframe M to Timeframe D
13. Undertake mobilization of different social communities/groups e.g. schools, religious groups on rights issues (campaigns, debates, music, easy compositions, drawings, sports) on PSEA. | bar: Timeframe M to Timeframe D
Indicators
1. Number of strategic meetings held.
2. Number of community awareness-raising activities conducted
3. Number of PSEA outreach services conducted with different social groups
4. FGD/assessment reports
5. Number of Organizations that have mainstreamed PSEA in their regular programmes
6. Number of Organizations who have signed PSEA code of conduct and statement of commitment on elimnation of SEA.
7.Number of donors who included commitment to PSEA in their contractual arrangement with partners
8.Copies of the SGB translated in Turkish and Kurdish languages
9.Number of coordination activities held with partners inside Syria
10.Stakeholders analysis report
11.Mapping reports
Means of Verification
1. Minutes of strategic meetings.
2. Activity reports.
3.Copies of translated awareness materials.
Outcomes/Result
1. Increased awareness among stakeholders on PSEA.
2. Increased involvement of stakeholders on PSEA activities.
3. Increased reporting of SEA cases.
4.Increased visibility for PSEA work among stakeholders.
PREVENTION FROM SEXUAL EXPLOITATION AND ABUSE
Objective 2: Increase stakeholders capacity to prevent Sexual Exploitation and Abuse. | [12 empty] | 1.Publisize names and contacts of PSEA focal persons to make them known to all stakeholders and communties. | DRHC's office, PSEA Coordinator, Participating Organizations and their partners, HLG, PSEA Network, PSEA/CBCM focal persons, affected communities, donors. | bar: Timeframe J to Timeframe D
2.Advocate for Organizations to ensure their staff sign code of conduct clearly prohibiting acts of SEA and obliging them to report such acts. | bar: Timeframe J to Timeframe D
3.Hold meetings with Human Resources of humanitaian actors/ organizations to advocate for strengthening /establisment of internal systems to prevent SEA including procedures guarding against hiring of persons who have a record of SEA offences. | bar: Timeframe J to Timeframe D
4.Sensitize and support Organizations to ensure inclusion and enforcement of codes of conduct on PSEA in cooperative agreements with implementing and operational partners, contractors, service providers. | bar: Timeframe J to Timeframe D
5.Facilitate the translation of the SGB in native Turkish and Kurdish languages. | bar: Timeframe J to Timeframe D
6.Develop IEC strategy for emerging PSEA issues. Design materilies . Stategy to disseminate suitable Design and production/printing of IEC materials | bar: Timeframe J to Timeframe D
7.Undertake assessement on SEA through data collection and analysis to establish actual or potential risk factors for vulnerability to SEA. | bar: Timeframe J to Timeframe D
8.Undertake training for stakeholders on PSEA in the field for commuinty leader including local councils, Imams,Teachers. | bar: Timeframe J to Timeframe D
9.Constantly identify and address capacity gaps on PSEA amongst actors at all levels through trainings. Assessments, surveys and evaluation. | bar: Timeframe J to Timeframe D
10.Identify and disseminate domistic and international best practices on PSEA. | bar: Timeframe J to Timeframe D
11.Support PSEA Focal persons to conduct inhouse training on PSEA for their staff. | bar: Timeframe J to Timeframe D
12.Support PSEA focal persons to collaborate with their human resource to incorporate PSEA in staff inductions. | bar: Timeframe J to Timeframe D
Indicators
1.Names and contacts of PSEA focal persons published.
2.Mapping Report.
3.Copies of translated SGB in Turkish and Kurdish languages and distributed
4.Activity reports
5.Number of Organizations who have incorporated PSEA in their partnership agreements
6.Number of Organizations who have incorporated PSEA in their staff inductions
7. Number of trainings conducted
Means of verifications
1.Names and contacts of PSEA focal persons.
2.Mapping Report.
3.The translated SGB
4. Minutes of meetings
5. Activity reports
6. Assessment report
Outcome/Results
1.There is ncreased number of stakeholders who are trained on PSEA
2. Increased number of Organizations have established internal PSEA prevention, reporting and investigative procedures
RESPONSE TO SEXUAL EXPLOITATION AND ABUSE
Objective 3: Strengthen response systems and capacity for improved service provision on SEA | [12 empty] | 1.Organize meetings with Organizations to promote use and or establishement of internal complaints and investigation procedures that are private and confidential for reporting SEA. | DRHC's office, PSEA Coordinator, Participating Organizations and their partners, HLG, PSEA Network, PSEA/CBCM focal persons, affected communities, donors. | bar: Timeframe J to Timeframe D
2.Carry out capacity assessment of existing complaint mechanisms and survivors assistance. | bar: Timeframe J to Timeframe D
3.Provide feedback to complainants and relevant stakeholders on the status of the cases they have reported. | bar: Timeframe J to Timeframe D
4.Create inter-agency community based complaints mechanisms that allows for complaints on a variety of issues, rather than only SEA, so as to promote use and avoid stigmatization. | bar: Timeframe J to Timeframe D
5.Provide referral of SEA cases to different service providers (health, psychosocial and investigation services). | bar: Timeframe J to Timeframe D
6.Train actors/service providers on their roles to effectively respond to cases of SEA. | bar: Timeframe J to Timeframe D
7.Follow up, monitor the complaint mechanism that are put in place to ensure that it is relevant to the needs of the people. | bar: Timeframe J to Timeframe D
8.Raising awareness for stakeholders on available services (how, why and where they can be accessed). | bar: Timeframe J to Timeframe D
9.Support Organizaions to mainstream PSEA in their ongoing work. | bar: Timeframe J to Timeframe D
Indicators
1.The Inter-Agency Community Based Complaints Mechanism
2.Capacity assessments undertaken
3.Number of referrals provided
4.Activity reports
Means of verification
1. The Inter-Agency Community Based Complaints Mechanism
2. Activity reports
Outcomes/Results
1. Increased reporting of SEA cases.
2. Increased number of survivors who access.
3. Improved knowledge of service providers.
MANAGEMENT AND COORDINATION
Objective 4: Enhance management and coordination of PSEA interventions. | [12 empty] | 1.Develop standards and operating procedures for the PSEA Network | DRHC's office, PSEA Coordinator, Participating Organizations and their partners, HLG, PSEA Network, PSEA/CBCM focal persons, affected communities, donors. | bar: Timeframe J to Timeframe D
2. Advocate, lobby and raise awareness on PSEA in accordance with the UN Secretary General's Bulletin. | bar: Timeframe J to Timeframe D
3. support heads of organizations to align their rules and regulations, HR policies, with PSEA code of conduct | bar: Timeframe J to Timeframe D
4.Lobby Organizations to nominate, commit and maintain dedicated PSEA focal persons to work in their own organizations and as Inter-Agency Network. | bar: Timeframe J to Timeframe D
5. Hold regular coordination meetings for the PSEA Network. | bar: Timeframe J to Timeframe D
6.Increase the profile of PSEA activities by providing timely reports and presentations on PSEA to humanitarian actors, HLG, SSG and to revelant bodies such as the IASC PSEA task force. | bar: Timeframe J to Timeframe D
7.Produce bi-annual PSEA Network News Letter | bar: Timeframe J to Timeframe D
8.Coordinate with IASC PSEA task team and other relevant bodies so as to keep them updated on Gaziantep's developments/mutual learning | bar: Timeframe J to Timeframe D
9. Develop a resource mobilization strategy for the PSEA network's program. | bar: Timeframe J to Timeframe D
10.Develop informationa sharing protocol
Indicators
1. PSEA Network SOP developed
2.Number of advocacy and activities with Heads of Institutions conducted
3. Number of donor advocacies conducted
4. PSEA News Letters produced
5.Number of Organizations with PSEA focal persons
6. Number of PSEA focal persons meetings held
7. Information sharing protocol developed
Means of Verification
1. The PSEA focal persons
2.The PSEA Network SOP
3. PSEA News Letters
Outcomes
1.Increased coordination with heads of Organizations on PSEA
2. Increased implementation of PSEA activities at individual Organizational level

## FPP
GAZIANTEP-CROSS BORDER PSEA IMPLEMENTATION
PSEA FOCAL PERSONS WORK PLAN
Overall objective: To reduce the prevalence of Sexual Exploitation and Abuse in Nothern Syria
PILLAR 1: ENGAGEMENT AND SUPPORT OF LOCAL COMMUNITIES
Objective: Increase engagement with and support to local communities on PSEA | Indicative Activities | Inputs
| 1. Organize and facilitate awareness at community level on their rights and entitlements, the fact that assistance should not be exchanged for sex or money | Focal Peron, his/her Organization, Management, PSEA/CBCM Network, HLG, DRHC
2. Conduct Focus Group discussions to get community information and feedback
3. Strengthening of community structures to deal with PSEA
4. Facilitate the signing of statement of commitment on prevention of SEA by local leaders
5. Develop and implement effective community PSEA workplan
PILLAR 2: PREVENTION OF SEXUAL EXPLOITATION AND ABUSE
Objective 2: Increase the knowledge and capacity of my organization and staff on PSEA preventions | Indicative Activities | Input
Focal Peron, his/her Organization, Management, PSEA/CBCM Network, HLG, DRHC
1.Raise awareness and on PSEA and code of conduct and expected beviour of staff for your Orgnization
2. Share the SG Bulletin and place copies on noitce boards
3. Facilitate signing of PSEA code of conduct by all staff
4. Share summary of your role and contact with all personnel and place copies on notice boards
5. Ensure active networking with other PSEA focal points
6. Support your Organization to put measures in place to check references and files of possible new hires to ensure no background of SEA
7. Ensure all contracts issued to implementing partners include clauses on SEA (SGB Section 6)
8. Develop organization-specific strategies to prevent and respond to sexual exploitation and abuse.
9. Incorporate all standards on sexual exploitation and abuse in induction materials and training courses for all personnel
10. Conduct orientation of new staff on PSEA
11. Map all your Organizations implementing and corporating partners, lobby them to establish PSEA focal persons and PSEA implentation strategy
PILLAR 3: RESPONSE TO SEXUAL EXPLOITATION AND ABUSE
Objective 3: Strengthen capacity and systems in my organization for improved response to SEA | Indicative activities | Input
Focal Peron, his/her Organization, Management, PSEA/CBCM Network, HLG, DRHC
1. Support your Organization to develop/strengthen internal PSEA reporting procedures for staff and other personnel.
2. Establish and publicize how your Organization’s personnel can report concerns or suspicions of SEA
3. Receive PSEA cases, record the cases on intake form and refer to relevant units/CBCM
4. Create awareness to your Organization on the inter-agency CBCM, how it functions and share contacts of all focal persons with staff and partners.
5. Facilitate strengthening of local community structures to report SEA issues
6. Advocate for investigations of all allegations of sexual exploitation and abuse in a timely and professional manner.
7. Provide feedback to the vulnerable communities on reported cases of PSEA
8. Conduct joint monitoring of imlementation at all levels.
PILLAR 4: MANAGEMENT AND COORDINATION
Objective 4: Provide support to the administration of my organization to implement their management and coordination role on PSEA | Indicative Activities | Input
Focal Person, his/her Organization, Management, PSEA/CBCM Network, HLG, DRHC
1. Assist the head of your Organization to fulfil his/her responsibilities in accordance with the SGB by preparing notes for him to share with staff, establishing internal mechanisms.
2. Support the inclusion of SGB standards in contractual arrangements with all implementing partners, suppliers of goods and services.
3. Share monthly and quarterly reports on PSEA with management of your Organization.
4. Coordinate your Organization’s adherence to monitoring/compliance mechanisms, including contributing report to the inter-agency PSEA/CBCM Network.
5. Track all PSEA-related activities for the Organization and ensure that all information on PSEA-related activities is shared with relevant persons in the Organization.
6. Keep data on reported incidents for general reporting and further development of efforts to address SEA in your Organization and to support the efforts of the PSEA Network.
7.Coordinate your Organization’s adherence to relevant monitoring/compliance mechanisms, including contribution to the annual report of the Secretary-General on Special Measures for Protection from Sexual Exploitation and Sexual Abuse.
8. Create a budget line for PSEA activities within the programmes and advocate for inclusion of PSEA budget in all departments.
9. Keep management up to date on PSEA measures taken and plans for future action.
10. Actively participate in networking with other PSEA/CBCM focal points and the Inter-Agency Network