Country-Level Action Plan to Prevent and Respond to Sexual Exploitation and Abuse

Malawi, 2024

The PSEA Country-Level model template outlines the priorities agreed by UNCT/HCT members to achieve jointly across countries with humanitarian[1], development and peace and security operations. This template provides the minimum requirements to review and analyse the effectiveness, impact, and progress on measures to prevent and respond to sexual exploitation abuse country wide. It serves as a model framework intended to be adapted and contextualized at the country level. The objective is to promote and document harmonized activities that contribute to implementing a robust action plan and provide the basis for tracking progress and provision/mobilization of required resources in related to PSEA in countries with United Nations presence. The action plan template should be regarded as a guiding tool, rather than a rigid form, allowing flexibility for customization according to the specific requirements of the context. Emphasis should be placed on addressing the components specified in the attached checklist (Annex II).

[Mandatory] Contact details of the PSEA Coordinator /Focal Point (Name, Entity, Email address): [If none, please indicate why?]

Lydia Fuliwa, Resident Coordinator’s Office, lydia.fuliwa@undp.org

[Mandatory] Contact details of the SVRO/FVRA/VRFP (Name, Entity, Email address): [If none, please indicate why?]

Overview

(Provide a brief overview of what is intended to be achieved in this Action Plan and indicate the challenges you might face in achieving).

The focus in 2024 is to deepen awareness of PSEA through a multifaceted approach that includes capacity-building, staff and community engagement, and strong partnerships. Tools developed/adopted in 2023 such as SOPs for recording and processing SEA complaints, Common Implementing Partner Assessment Tool, The GBV referral Pathway, the Code of Conduct for Humanitarian Actors, will be put to full use in the coming year. The expected results are an  increased awareness and understanding of PSEA and also empowered communities that are in a position to prevent and respond effectively to these issues.

[1] This applies to refugee and humanitarian context which could be sub-national or regional in nature.

| Desired outcomes | Indicators | Targets / Benchmarks | Key actions | Timeframe (Quarter / Year) | Budget / Funding Source | Lead agency(ies) per activity/ Status & outrach |
| --- | --- | --- | --- | --- | --- | --- |
| Part A: Priority prevention outcomes for PSEA |  |  |  |  |  |  |
| Outcome 1. Prevention. All United Nations staff and related personnel know the UN standards of conduct for protection from sexual exploitation and abuse and understand their personal and managerial/ command responsibilities to address sexual exploitation and abuse and other misconduct. |  |  |  |  |  |  |
| Output 1.1 Personnel understand the United Nations standards of conduct on the protection from sexual exploitation and abuse. | - All UNCT/HCT personnel, including those visiting the country, are provided with an induction briefing on conduct and discipline issues, including sexual exploitation and abuse. | Reminders are communicated to all staff to ensure on-going visibility/awareness of the entity’s policies. SOPs address out-of-bound areas. All visitors/consultants/contractors are informed on country policies and SOP. | Quarterly reminders to staff on UN Policy on SEA In-person PSEA refresher orientation to all staff PSEA presentations during all staff Town Hall on Concepts, Principles and Reporting Pathways PSEA as a Standing Agenda during staff weekly meetings PSEA Knowledge Checks for staff during ASM Sharing of PSEA Online Courses for all staff Continuous reminders to staff on PSEA during all-staff meetings and through bi-monthly email broadcast PSEA orientation for ILO staff on United Nations standards of conduct on the protection from sexual exploitation and abuse Training for FAO partners on United Nations standards of conduct on the protection from sexual exploitation and abuse PSEA in-person awareness sessions to UN Satelite offices | On going Biannual Biannual Weekly Monthly/Quarterly Biannual Monthly/bi-monthly Bi-annual Biannual Annual Biannual | No cost No cost No cost No cost No Cost No cost No cost NO Cost No cost TBA 3,300 | Each Agency RCO RCO/Each Agency UNAIDS UNICEF RCO, All Agencies UNHCR UNHCR ILO FAO, RCO RCO, all Agencies |
|  | - Prevention measures such as curfew/off-limits policies operate in peace operations and consideration is given to implementing such measures to other duty stations |  | N/A | N/A | N/A | N/A |
|  | - The UNCT/HCT personnel know the standards on sexual exploitation and abuse (training, leadership dialogues, town-halls). | Regular meetings and awareness discussions take place. PSEA awareness-raising materials (broadcast, pamphlet, posters, etc.), including “no excuse cards” are locally contextualized, produced and distributed. | Print posters, banners, No Excuse Cards and share with UN staff | Q1 2024 |  | Each Agency, WHO, FAO, UNFPA, ILO, UNAIDS, UN Women, UNDP, UNHCR |
|  | - All personnel are aware of the policy for protection against retaliation for reporting misconduct – to empower, encourage and protect staff who report cases of sexual exploitation and abuse (ST/SGB/2017/2/Rev.1). | UNCT/HCT staff members are aware of their obligation to report sexual exploitation and abuse/ misconduct and the policy for protection against retaliation. | Quarterly briefings on PSEA and Policies of each agency UNCT Enforce Mandatory PSEA training Focal Points orient of new staff on PSEA | No cost Biannual Q1, ongoing | Ongoing TBD No cost | Each Agency RCO, Each Agency Each Agency |
|  | - All personnel are provided with clear guidance on where and how to report allegations of misconduct. |  | PSEA onboarding sessions with all new personnel Broadcast email on PSEA reporting | Ongoing Quarterly | No cost No cost | Each Agency Each Agency |
| Output 1.2 Leadership, managers and commanders know their personal and managerial/command responsibilities to address misconduct and are aware of the procedures, rules and actions required to respond to incidents of misconduct. | - Managers monitor completion by all personnel in country of mandatory online and classroom training. | Monitoring mechanisms are in place and working. | Focal points coordinate with HR to ensure 100% compliance of the mandatory courses Quarterly reminders from Focal points on mandatory courses Regular engagement of Representative and senior managers with PSEA focal points for updates on PSEA activities (checklist for representatives and senior managers). | Quarterly Jan, Apr, Jul, Oct monthly | No cost No cost No cost | Each Agency RCO, Each Agency UNHCR |
|  | - Leadership communicates regularly and in varied formats in order to increase awareness and instil trust in the policies, including broadcasts on the duty to report misconduct. | Meetings with staff are convened to review implementation of country level sexual exploitation and abuse (townhall, leadership dialogue, etc.). | Follow-up on Biannual virtual discussion on PSEA implementation PSEA is a Standing Agenda during monthly staff meeting | June, December Ongoing | No cost No cost | RCO, Each Agency UNAIDS, UNESCO |
| Output 1.3 Quality training of personnel/awareness-raising on sexual exploitation and abuse policies is conducted regularly. | - All UN staff and related personnel complete the mandatory in-year refresher training and/or awareness briefings to personnel are conducted. Substantiation is done for those not completing the training. | Induction training for all personnel is conducted at regular intervals. | Focal points conduct PSEA induction for new staff and short time consultants Briefing of Humanitarian teams on PSEAH | Quarterly As need arises | No cost 5,700 + | Each Agency RCO, FAO, WFP, UNHCR, UNFPA UNICEF, IOM, UN Women, UNODC |
|  | - UNCT/HCT leaders certify that all allegations of sexual exploitation and abuse relating to areas within their responsibility have been accurately and fully reported. | 100% response to the resident/humanitarian coordinator. | Focal points update UNCT on numbers of allegations of SEA | Monthly | No cost | RCO, all Agencies |
| Part B: Priority response outcomes for PSEA |  |  |  |  |  |  |
| Outcome 2. Safe and accessible reporting. Every child and adult recipient of United Nations assistance has access to a safe, gender and child-sensitive pathways to report sexual exploitation and abuse (including through community-based complaints mechanisms) that lead to assistance, are appropriate to the context and accessible to those in the most vulnerable situations). |  |  |  |  |  |  |
| Output 2.1. Safe, accessible, gender and child-sensitive mechanisms are in place for reporting sexual exploitation and abuse, particularly in high-risk areas. | a. UNCT/HCT Inter-agency SOPs on community-based complaint mechanisms and/or networks (CBCM/CBCN) on PSEA are established following inclusive consultations with all relevant stakeholders, including communities, disseminated and rolled out, and appropriate staff trained. | Interagency CBCM/CBCN Standard Operating Procedures (SOPs) are endorsed by all UNCT/HCT members. | Sharing of PSEA SOPs with Focal Points Orienting PSEA In-Country Network on PSEA SOPS Joint review of effectiveness of CBCFM | January Quarterly Q1-Q4 Annual | No cost TBD 4240 + | RCO, all Agencies RCO, All Agencies, Protection Cluster All Agencies, RCO |
|  | b. A variety of reporting channels appropriate to the local context is in place to fill reporting gaps as identified by mapping. | Regularly updated mapping of existing complaint and feedback mechanisms in the response. Multiple confidential reporting channels are available which cater to the diversity of the population and differing levels of access (PWD, Older Persons, children). | Coordinate with the GBV subcluster & Protection Cluster on availability of CFM in camps and other disaster areas Coordinate with OCHA on statistics of CFMs and locations Capacity building of protection actors managing CBCMs Strengthen referral pathways through training personnel Update existing complaint and feedback mechanisms. Awareness sessions on existing CFM and referral pathways. | Q1 2024 Q2, Q3 Biannual Ongoing Ongoing | No cost TBD TBD TBD TBD | RCO, Each Agency Each Agency Each Agency Each Agency Each Agency |
|  | c. Percentage of children and adults which have access to a safe channel to report sexual exploitation and abuse. | E.g., 100% of the affected population have access to at least one (1) safe and accessible channel to report sexual exploitation and abuse. | Assess the accessibility of current reporting mechanism & strengthen reporting mechanism Conduct Risk Assessment in implementation areas Map and Strengthen referral pathways Strengthening of available CBCM through orientation of protection actors Develop and share SOPs on CP, GBV, PSEA, Protection guidelines | Q1 2023 ongoing Q2 Q3 ongoing | TBD 8000 TBD TBD TBD | All Agencies RCO through GBV Sub Cluster GBV Cluster, Each agency WFP, WHO, UNFPA, UNICEF, IOM, UN Women, UNODC RCO & Protection Cluster Co-Lead (UNICEF) |
|  | d. Percentage of allegations reported to the PSEA Network per month and responded to within seven days (Disaggregated by age, sex, and type of complaint (less than 18; 18 and above). |  | Generate Monthly report for RC on SEA allegations Strengthening of available CBCM through orientation of protection actors | Quarterly ongoing | TBD TBD | RCO, All Agencies UNICEF |
| Output 2.2. Community mobilisation, consultation and awareness-raising on PSEA in each community receiving and/or affected by United Nations assistance. Where there is an HC/HCT this would apply to all humanitarian partners. | - Number of adults and children (disaggregated by gender and age) reached through consultation in the establishment of community-based complaint mechanisms, awareness activities and community mobilisation interventions on PSEA, including how to report SEA-related complaints. | E.g., Consultations with affected population inform the establishment of CBCMs. Evaluation of existing CBCMs for effectiveness and compliance with human rights principles. | Ensure CBCM is in place in all target districts Focal points incorporate consultations in PDMs/other assessments Support the updating of online referrals and CBCM | Q2 2023 Q2 Ongoing | TBD No cost No cost | Each Agency WFP UNFPA, RCO |
|  | - Percentage of sites reached by PSEA communications materials, how to report sexual exploitation and abuse and how to access victim/survivor-centred assistance. (disaggregated by type of PSEA communication materials developed for each population group identified). | 100% of sites provide information on the prohibition of sexual exploitation and abuse, how to report and receive assistance. Age and gender-sensitive materials on how to report sexual exploitation and abuse and how to access victim/survivor-centred assistance developed and disseminated. | Distribute IEC materials in all project sites Community radio jingles Produce & distribute PSEA leaflets & posters including children and large prints for people with visual impairment Incorporate PSEA in new projects at district and community levels Conduct community awareness sessions Establishment of complaints boxes in displacement sites Training of community structures on PSEA | Q3 Q1 Q2 Ongoing February Annually | 3000 20000 No cost No cost TBD existing partner budgets | FAO, IOM, UNESCO Each Agency Each Agency FAO, IOM Each Agency Each Agency UNHCR |
|  | - Number of individuals within the affected population (disaggregated by age and gender) reached with key messages and awareness-raising material on PSEA. |  | Conduct awareness through FFS and district level gender technical working groups Update RCO on reported cases. Awareness/outreach sessions for communities including CSOs | All Quarters in 2024 Ongoing Ongoing | No cost No cost Within existing budget and program sites(partner) | FAO, UNESCO Each Agency UNHCR/ UNAIDS |
|  | - Community perceptions and communication preferences are captured on a regular basis (informally and formally through needs SEA risk assessments, surveys, focus group discussions, etc.), and used to improve services. |  | U reports | Dec | TBD | UNICEF |
| Outcome 3. Victims’ right to assistance. Every child and adult victim/survivor/complainant is offered immediate, quality assistance (medical care, psychosocial support, legal assistance, reintegration support). |  |  |  |  |  |  |
| Output 3.1 Sexual exploitation and sexual abuse victim/ survivor assistance is provided through Gender-Based Violence (GBV) or Child Protection (CP) programming which is familiar with sexual exploitation and abuse and the specific needs of victims/survivors. In humanitarian context, this may be resourced through the Humanitarian Response Plan (or other funding mechanisms). In other settings, UN entities should consider the creation of a contingency fund to facilitate victims’ rights support and assistance, including through exploring opportunities for joint fundraising by United Nations Country Team members and project proposal submitted to the Trust Fund in Support of Victims of Sexual Exploitation and Abuse. | - Mapping of the existing service providers (e.g., GBV and CP programming) and current gaps in SEA assistance coverage are identified and addressed. |  | Dissemination of PSEA SOPs to GBV referral points Retreat for PSEA Focal Points to enhance coordination among Agencies PSEA service provider Mapping exercise to Identify gaps in SEA assistance and provide support | Ongoing Ongoing Q3 | No Cost 4,800 TBD | RCO, Each Agency RCO UN Women, WHO |
|  | - Number and percentage of SEA victims/survivors/complainants who have been promptly referred to quality assistance, as part of ongoing GBV and CP programming. | E.g., 100% of victims/survivors are referred for assistance and received support within 48 hours. Data are disaggregated according to the affiliation of the offender (UN staff and related personnel and implementing partners). | Generate reports for referrals Dissemination of SOPs for victims assistance to CBCMs | Monthly March 2024 | No cost TBD | RCO, Each Agency Each Agency |
|  | - Number and percentage of SEA victims/survivors who have accessed to assistance (disaggregated by age and gender and type of assistance received). | E.g., 100% of victims/survivors are referred for assistance and received support within 48 hours. Data are disaggregated according to the affiliation of the offender (UN staff and related personnel and implementing partners). | Coordinate with YONECO and District Social Welfare Office on SEA data Monitor the use of GBV registers in the service provision points Capacity building of Community Based service providers Monitor implementation of victim-centred approach using client feedback surveys | Monthly Ongoing Ongoing | No cost TBD TBD 4240 + | RCO, UNICEF UNFPA, All Agencies Each Agency, UNICEF UNHCR, RCO, all Agencies |
|  | d. Percentage of the affected population, particularly women and children, that can access GBV assistance. | E.g., 100% of the affected population (esp. women and children) can access GBV services. e.g., Number of people satisfied with assistance received following a complaint of sexual exploitation and abuse. | Develop partnerships with key UN agencies- UN Women, UNFPA, UNICEF | Q1 |  | WFP |
|  | - Funding/resources for assistance to victims/survivors of sexual exploitation and abuse is available. (Please indicate if there are any funds of this nature) | There is a joint/contingency/ dedicated fund or pooled resources at country level. | Submit Coordinator’s budget to UNCT Submit proposal to Trust Fund | Q3 | No cost | RCO, All Agencies |
| Output 3.2 PSEA Networks have referral pathways for victim/survivor assistance in place, as part of an integrated approach with GBV services. See Technical Note on the Implementation of the UN Protocol on the Provision of Assistance to Victims of SEA | - Status of implementation by PSEA Network of protocol for referral and provision of services for sexual exploitation and abuse victims/survivors (in line with GBV referral pathways). | E.g., GBV referral pathway integrated within PSEA Network SOPs. | Disseminate PSEA SoPs to IP, government departments | Q1 | No cost | RCO, Protection Cluster, GBV Sub Cluster, Each Agency |
|  | - Tracking and data collection on victims and victim assistance (please indicate the system in place, what information is collected and frequency of maintenance). | Please indicate if Gender-Based Violence Information Management System (GBVIMS) is being used to maintain data on sexual exploitation and abuse or indicate if there is a dedicated tracking system in place/under development. | Strengthen GBVMIS | Ongoing | TBD | UNFPA |
| Outcome 4. Accountability and investigations. Every child and adult victim/survivor of sexual exploitation and abuse who is willing has their case investigated in a prompt, and safe way in accordance with a victims’/survivors’ rights approach. |  |  |  |  |  |  |
| Output 4.1 PSEA Networks adopt, implement and track progress against uniformed protocols/guidelines for prompt, safe and victim/survivor-centred assistance during investigations at country-level. | a. Percentage of UNCT/HCT members understand the standards under investigations are conducted. |  | Conduct Training of Trainers in PSEA Investigations | Q1 | 19,550 | UNICEF, RCO |
|  | b. PSEA Network members and local partners have personnel trained on SEA guidelines and protocols for victim/survivor-centred investigations. |  | Focal points conduct IP PSEA Assessment using Common IP Tool Focal points conduct orientation with partners on protocols for survivor centred investigations | Q1-4 Ongoing | TBD 10000 | Each Agency UNICEF, RCO, Each Agency |
| Output 4.2 Sexual exploitation and sexual abuse victims/survivors informed of and/or supported in relation to investigations and accountability processes. | - Percentage of victims/survivors who are informed of the outcome of the investigations. |  | Coordination Meetings with AAP group to ensure that 100% of victims are given feedback Feedback with survivors to identify gaps and offer further support | Q1-Q4 Ongoing | TBD No cost | RCO, Each Agency Each Agency |
| Output 4.3 When working with implementing partners, adequate safeguards are in place and action is taken related to sexual exploitation and abuse – e.g., screening, cooperative arrangements, monitoring, and termination of arrangements (United Nations Protocol on Allegations of Sexual Exploitation and Abuse Involving Implementing Partners; ST/SGB/2003/13). | - The UNCT/HCT has policies on reference checking and vetting for former misconduct or supervision and performance appraisals related to UN Implementing Partner PSEA Capacity Assessment and they are shared with UNCT/HCT. | E.g., Job applicants and contractor personnel are screened for history of misconduct/SEA issues before recruitment (The Clear Check and/or the Inter-Agency Misconduct Disclosure Scheme are consulted, self-certified declarations of previous offences, allegations and disciplinary history are required. | Focal points work with HR to ensure screening of candidates is done prior to offer of employment Conduct trainings for implementing partners in the Central, South and Northern regions targeting the Head of Government departments and senior Managers for partner organisations to create awareness and ensure that their staff members are aware of the policy | Ongoing Q1- March 2024 | No cost 10,000 | Each Agency UNDP, UNICEF, Each Agency |
|  | - UN Implementing Partner PSEA Capacity Assessment guidelines are implemented. | Implementing partners assessment are centralized at country level and shared with other members of the UNCT/HCT. | Share Common Implementing Partner Assessment Tool with all Agencies Orient focal points on Common IP Assessment Tool Conduct IP Assessment for UN Partners | Q1, Q3 Ongoing Quarterly | No cost Virtual TBD | UNICEF, RCO UNICEF, Each Agency UNICEF, UNFPA, Each Agency |
|  | - Follow-up is established for the implementing partners that do not meet the minimum threshold. | Actions in line with the implementing partners protocol are taken against those implementing partners that do not meet the required standards. | PSEA Monitoring visits to project sites Drawing supportive plans to partners failing short on PSEA minimum standards | Ongoing Ongoing | 4240 + TBD | Each Agency Each Agency |
| Part C: PSEA Country-Level Structure |  |  |  |  |  |  |
| Outcome 5. PSEA inter-agency country-level structure. The Resident/Humanitarian Coordinator and UNCT/HCT are supported at senior management and technical-levels to lead, oversee, and deliver on the above four PSEA Outcomes. |  |  |  |  |  |  |
| Output 5.1 The role of the RC/HC as PSEA lead is clear to all PSEA stakeholders. | - The RC/HC takes an active lead on PSEA and, where relevant, coordinates with the (D)SRSG. | RC/HC circulates code of conduct or the IASC Six Core Principles statement of purpose on PSEA. RC/HC supports implementation and monitoring on in-country PSEA Strategy, making explicit the leadership role of the RC/HC and UNCT/HCT. | Circulation of the workplan for UNCT Malawi approval Harmonization of Tools to enhance a common approach and advance the; “One UN Agenda” Town Hall session on PSEA concepts, principles and reporting pathways Quarterly Coordination Meetings for In-Country Network Monthly Coordination meetings for Inter-Agency Network | November 2024 Ongoing Biannual Monthly | No cost No cost No cost TBD Virtual | RCO RCO RCO RCO RCO |
|  | - Country Directors/ Representatives share appropriate information with the senior most UN Official in-country immediately when they become aware of an SEA allegation involving UN staff and related personnel where there is sufficient information to identify an act of SEA against an identifiable perpetrator or identifiable victim. | Country Directors/ Representatives share the information in line with the annex found in the Guidance Note to UN Entity Field Operations on Sharing Incident Information on Sexual Exploitation and Abuse with the Senior Most UN Official in-Country | UNCT Orientation on PSEAH | Q1, Q3 | No cost | RCO, UNAIDS |
| Output 5.2 Members take on the PSEA role to support the Resident/Humanitarian Coordinator to deliver on PSEA at the UNCT/HCT level and the PSEA Network at the technical level. | - Status of the designation of agency chairs for the PSEA Steering Committee (principal level, UNCT/HCT) and the PSEA Network (technical level). |  | Update list for Focal Points from Agencies | Biannual | No cost | RCO |
| Output 5.3 A full-time PSEA Coordinator (with medium to long-term secured funding) is in place, with a direct reporting line to the HC/RC, to provide day-to-day technical support and expertise to the inter-agency PSEA Network. In the absence of a Senior Victims Rights Officer (SVRO) or Field Victims’ Rights Advocate (FVRA), consider the designation of a Victim’s Rights Focal Point (VRFP) at the country level by the PSEA Network in consultation with the most senior United Nations official in the country. | - Status of deployment of a full-time PSEA Network Coordinator (with clear ToRs). See generic ToRs at Link | P4 level full-time PSEA Coordinator is in place PSEA Coordinator reports directly to the RC/HC. | completed | completed | completed | completed |
|  | - The PSEA Coordinator takes an active lead in supporting senior leadership in developing and implementing PSEA Network TORs and a PSEA Work Plan, based upon the inter-agency PSEA Network risk assessment. | A SVRO/FVRA or a VRFP has been appointed at the country level in the Office of the HC/RC. | Capacity building of PSEA In-Country Network members | Ongoing | TBD | UNFPA, RCO, Agencies |
|  | - On request, the PSEA Coordinator provides expert guidance and technical support to Network members and other relevant entities operating in the context to strengthen their internal PSEA programs in line with good practice and standards. |  | Capacity building of National PSEAH Network Retreat of UN PSEAH Network | Q2 annually | 10,000 4800 | RCO RCO |
|  | d. Creation of a SVRO position or designation of the FVRA or consider the designation of a VRFP in the office of the HC/RC with a system-wide mandate has been appointed to advise at the country level (please indicate date of appointment or a timeline if the appointment of a SVRO/FVRA/focal point with a system-wide mandate is in the process, grade level and source of funding if full-time SVRO). See generic ToRs on the Knowledge Gateway (Link) under the tab Victims’ Rights |  |  |  |  |  |
| Output 5.4 An inter-agency PSEA Network is in place with the resources and expertise necessary to deliver on PSEA outcomes (above). | - PSEA Network being established or in place. | E.g., PSEA Network is established and reports regularly to RC/HC via the PSEA Coordinator. PSEA Network includes all UNCT/HCT members, including representation from international and national NGOs. | Monthly updates to RC Management Letter form RC to OSCSEA | Ongoing Annually | no cost no cost | Agencies, RCO RCO |
|  | - All the PSEA Network members have received training from their entities on PSEA. |  |  |  |  |  |
|  | - Integration of PSEA in the Humanitarian Response Plan (or similar), where relevant. | E.g., PSEA Action Plan is costed and resourced through HRP. | PSEA Action Plan is costed and resourced through UNCT | Ongoing | No cost | RCO |
|  | - All organisations (UNCT/HCT and PSEA networks) meet required minimum standards such as the Minimum Operation Standards (MoS) and Core Humanitarian Standards (CHS) PSEA Index to enable appropriate complaints receipt and handling. | All UN partners meet the requirements in the UN common assessment. Joint capacity development and training provided through the network to support entities to meet the PSEA requirements. | RCO to share & orient focal points on Common IP assessment Tool Conduct IP Assessment Monitoring visits to project sites on PSEA recommendations | Ongoing Ongoing | Virtual | RCO, Each Agency Each Agency |
|  | - Status of development and implementation of the UNCT/HCT PSEA Action Plan, including clearly defined roles and responsibilities of each actor. | E.g., PSEA Action Plan is endorsed by all UNCT/HCT members. | Plan developed by 30 November 2024 | Q4 | TBD | RCO |
| Output 5.5 PSEA technical focal points from all UNCT/HCT members are in place and actively contribute to the PSEA Network’s delivery of PSEA outcomes (as per the above). | - Percentage of UNCT/HCT members that have appointed a dedicated PSEA technical focal point to the PSEA Network (with clear ToRs). |  | Conduct PSEA Training for sectoral PSEA Focal Point | Q2 | no cost | UNICEF |
|  | b. The PSEA technical focal points are active in designing or disseminating awareness-raising tools and facilitate events for community members with emphasis on their rights |  | Conduct community meetings on PSEA -Produce IEC materials and conduct awareness sessions with beneficiaries - | Q2 and 4 Q1 to Q4 | 5000 | Each Agency WFP, UNFPA |
|  | c. The PSEA technical focal points are actively working with the inter-agency PSEA Network to establish a CBCM/CBCN |  | Attend PSEA network meetings/trainings | Q1-Q4 | Virtual | Each Agency |
| Output 5.6 Country-level risk assessment in respect of sexual exploitation and abuse conducted on the basis of risk management tools | - The inter-agency PSEA network carries out regular SEA risk assessments and shares the findings and recommendations with the UNCT/HCT. |  | Conduct PSEA risk assessment in targeted districts Conduct PSEA risk Assessment for UNICEF IPs | Q2 | 2920 + | Each Agency UNICEF |
|  | - The inter-agency PSEA network provides technical support needed to mitigate risks of SEA, in collaboration with relevant stakeholders. |  | Provide guidelines on mitigating SEA risks with implementing Partners District Councils and Civil Protection Committees | Q1 | No cost | Each Agency, WFP |
|  | - The risk is regularly assessed and updated. |  |  |  |  |  |

For additional information and resources:

- Management and accountability of the UN Development and Resident Coordinator System

- Knowledge Gateway

- Inter-Agency Standing Committee resources

  - IASC Six Core Principles Relating to SEA (Revised 2019)

  - IASC Minimum Operating Standards PSEA

  - Guideline – Inter-Agency Community-Based Complaint Mechanisms – Protection against Sexual Exploitation and Abuse

- Guideline – Inter-Agency Community-Based Complaint Mechanisms – Protection against Sexual Exploitation and Abuse

- UN System Policies and Protocols on PSEA

- UN System Tools on PSEA

- Office of the Victims' Rights Advocate

This applies to refugee and humanitarian context which could be sub-national or regional in nature.

[2] The targets provided in the model template are intended as illustrative examples. Actual targets would need to be determined at country-level.

[3]}United Nations staff and related personnel include United Nations staff members, consultants, individual consultants/contractors, interns, national officers, United Nations volunteers, experts on mission and contingent members.

[1] Type of mechanism and targeted locations to be determined by each UNCT/HCT based on context and existing channels/mechanisms for reporting already functioning. These could include, for example, phone hotlines, SMS, PSEA focal points, service points, etc. This could involve broader complaint channels that are strengthened with the necessary safeguards for reporting sexual exploitation and abuse, or training of PSEA focal points within protection-related services to support reporting and referrals, and/or other systems, and/or a combination of the above, as appropriate per the country context.

[2] Community-Based Complaint Networks (CBCNs) support communications with complainants and victims while allegations are being investigated, facilitate the provision of assistance and support to victims and their reintegration into their communities. The UN has engaged with local and international organizations and representatives of communities to develop formal and informal structures and channels that are safe, confidential, and easily accessible to women, men, girls and boys to report misconduct, specifically sexual exploitation and abuse, and follow up on the status of reported incidents and receive support.

Access would be defined within the country context taking account of the type of complaint channels in place. This could include, for example, report to individual directly, phone access, taking account of age, gender, literacy, disability, etc., and/or a combination of factors. Please also note that this indicator refers to the estimated coverage of the population by the CBCM.

This indicator is intended to allow HCs/HCTs to track and measure the use of SEA-related complaint channels by affected populations, including by those who are most vulnerable, as a core component of their overall effectiveness. This indicator is to be read together with related indicators to understand the overall accessibility, trust in, and effectiveness of SEA-sensitive complaint channels by and for affected communities. It is not intended to replace or duplicate the external reporting obligations that agencies hold, for example the UN reporting of sexual exploitation and abuse allegations to the UN Secretary-General on a quarterly basis.

This should include the consultation of communities, particularly women and children, in the design of SEA-sensitive community-based complaint mechanisms.

Support to victims/survivors/complainants is unconnected with the investigation and should be pursued from the time of an allegation as indicated in the UN Comprehensive Strategy on Assistance and Support to Victims of Sexual Exploitation and Abuse

This can and should include f existing protection system which provides the basis for support to sexual exploitation and abuse victims/survivors.

The tracking of access to services is a core function of the PSEA Network’s role in strengthening response to sexual exploitation and abuse. Current gaps in SEA assistance coverage (as provided through GBV/ CP programmes) should be systematically addressed by UNCT/HCT members, as well as through CERF/CBPFs. There should be a tracking system maintained by the UNCT

See the UN Protocol on the provision of assistance to victims of sexual exploitation and abuse (“UN Victims’ Assistance Protocol”), 12 Dec 2019. This could include, for example, the inclusion of reference and procedures for referrals and accessing services.

This may include civil and criminal proceeding, as well as other redress measures.

Senior most UN officials in-country include Resident and Humanitarian Coordinators (RC/HC), Special Representatives of the Secretary General (SRSG) and Heads of Mission (HOM).

Generic ToRs for a focal point for victims’ rights is available from the Office of the Victims’ Rights Advocate (ovra@un.org).