## Sheet1
Completed
Ongoing
Not started yet
Inter-agency Work Plan - Prevention of Sexual Exploitation and Abuse (PSEA)- South Sudan 2018
Thematic Area | Activities | Timeline |  |  |  | Budget | Source of funds | Lead agency | Supporting agencies | Progress | Comment
|  | Q1 | Q2 | Q3 | Q4
1.Coordination and Engagement | 1. Appoint dedicated PSEA focal Person in each agency and regularly update the Focal Point list (National and field level) | X | X | X | X | 0 | N/A | All members
| 2. Hold regaluar orientation sessions for new PSEA TF members |  | X | X | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN | RCO
| 3. Conduct monthly PSEA TF meetings | X | X | X | X | 0 | UNFPA/UN WOMEN | Co-Chairs UNFPA/UN WOMEN |  |  | Refreshments and material for the TF meetings
| 4. Conduct regular teleconference with global PSEA Taskforce for advice, sharing of practices and lessons. | X | X | X | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN
| 5. Implement 7-Point Leadership Action Plan | X | X |  |  | 0 | N/A | All agencies |  |  | Decided by the UNCT
| 6. Establish Field-level PSEATaskforces in minimum 18 locations |  |  | X | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN | All other agencies |  | ToRs for FPs adaptable to local needs. ToR should also include CBCM lead role.
| 7. Conduct High Level discussion at HCT/UNCT/SMG level on accountability mechanisms for PSEA | X | X | X | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN
| 8. Develop a Communication Strategy on PSEA. |  |  | X | X |  |  | Co-Chairs UNFPA/UN WOMEN | RCO |  | Agency lead and support needs to be confirmed
| 9. Conduct Media Engagement |  |  |  | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN
2. Protection from SEA | 1. Conduct Risk Assessment for SEA in the selected fields/ locations e.g. PoCs. | X | X | X | X | 2500 | UNCT Cost-shared | All members
| 2.Translate english outreach material into relevant local languages | X | X | x |  | 0 | N/A | IOM, UNFPA
| 3. Conduct ongoing and annual PSEA campaigns through community outreach and public information measures – at national and local level | X | X | X | X | 5000 | UNCT Cost-shared | All members
3. Capacity Building | 1. Organize inter-agency training on CBCM for Focal points from UN agencies | X | X | X | X | 8500 | UNCT Cost-shared | All members
| 2. Conduct PSEA training for NGOs | X | X | X | X | 0 | N/A | N/A
| 3. Facilitate Training of Uniformed Personnel on PSEA (Police and military) | X | X | X | X | 0 | N/A | N/A
| 4. Organize Training of Trainers (ToT) for field specific personnel including UN, UNMISS, and other partners (NGOs) to roll out PSEA capacity in South Sudan | X | X | X | X | 0 | N/A | N/A
| 5. Train Women and Girls Friendly Space staff on SEA survivor assistance and complaint referral procedure | X | X | X | X | 0 | N/A | N/A
4. Mechanism to report and respond to SEA | 1. Activate internal and external community-based complaint & referral mechanisms within all UN entities and partners (including common hotline and common email for reporting SEA, complaint intake form and improved face-to-face reporting). | X | X |  |  | 55 000 | UNCT Cost-shared (5 000) and agency funds (50 000) | UNICEF | All other agencies |  | UNICEF: $50,000 partnership being developed with ACTED forPSEA activities including CBCM in Juba POCs and $50,000 partnership being developed with DRC for PSEA activities including CBCSM in Malakal POC
| 2. Ensure that CBCM field team receives training and staff turnovers are covered by new training. | X | X | X | X | 0 | N/A | Lead agencies of each CBCM | All other agencies |  | It needs to be decided if all CBCM Team members should be trained in Case Management or only some of them (e.g. some reporting, some referral)
| 3. Ensure that contact details of all CBCM team members are up-to date in order to support field missions |  | X | X | X | 0 | N/A | RCO, with support of all lead agencies | All other agencies
| 4. Ensure appropriate case management tools including log and database | X | X | X |  | 0 | N/A | IOM, UNFPA, UNICEF, UNMISS |  |  | IASC PSEA database could be piloted for a 3 Month testing period set May to July, 2 locations with good internet connectivity, 2 locations with poor internet connectivity
5. Advocacy | 1. Advocate for NGOs to strengthen their efforts on PSEA through ie participation in PSEA TF and UN accountability mechanisms | X | X | X | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN | OCHA |  | OCHA is supprting with developing AWP for NGOs on PSEA
| 2. Provide briefs and updates UNCT, HCT, Department of Peace Keeping Operations (DPKO) & Senior Management Group (SMG) on PSEA. | X | X | X | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN
| 3. Provide briefs and updates to Victims’ Rights Advocate for South Sudan | X | X | X | X | 0 | N/A | Co-Chairs UNFPA/UN WOMEN
6. Monitoring and Reporting | 1. Produce quarterly and annual report on PSEA in South Sudan to HQ | X | X | X | X | 1500 | UNCT Cost-shared | RCO | All other agencies
| 2. Institutionalise feedback mechanisms on lessons, and experience to agencies and partners generated by M&E activities, including M&E joint field missions | X | X | X | X | 2500 | UNCT Cost-shared | All agencies | RCO
Total | [5 empty] | 75 000