## 2019 workplan with updates
Completed | Inter-agency/HCT taskforce Work Plan - Prevention of Sexual Exploitation and Abuse (PSEA)- Somalia 2019
Ongoing
Not started yet
Thematic Area | Activities | Timeline |  |  |  | Budget | Source of funds | Lead agency | Other agencies | Progress | Comment
|  | Q1 | Q2 | Q3 | Q4
1.Coordination and Engagement | 1. Appoint dedicated PSEA focal Person and regularly update the Focal Point list (National and field level) | X | X | X | X | 0 |  | Co-chairs |  |  | National level: Agencies have completed identification of Focal points at national level. Some yet to share the contacts of the alternate FP Field level: IOM has finalized identification of PSEA champions in the field locations. UNHCR is in the process of appointing focal points at field level (appointed in Baidoa and Bossaso, remaining offices pending) Q2: The contact list of focal points updated with the current changes in some agencies. It was shared with the taskforce members to confirm. Q3: Contact list updated and expanded to include field level focal points
| 2. Recruit a PSEA Taskforce coordinator | [6 empty] | IOM, UNHCR |  |  | PSEA taskforce coordinator reported in December 2018.
| 3. Conduct monthly meetings of PSEA task force focal points | X | X | X | X | 0 |  | Taskforce Coordinator |  |  | Taskforce meetings held and minutes taken: Dec 18. 2019: Feb, Mar, May,Jun, Jul, Aug, Sep, Oct, Nov & Dec
| 4. Conduct regular teleconference with global PSEA Taskforce for advice, sharing of practices and lessons. | X | X | X | X | 0 |  | Co- chairs |  |  | Q1: Held regular email communication with Alexandra, PSEA-CBCM coordinator IOM/IASC. Q2: Coordinator was part of the global deliberations in Geneva that revised and developed a generic TOR for PSEA Coordinator; developed training contents for future PSEA coordinators. Alex (IOM Geneva) to support Somalia in Q3 Q3: Regular communication with global PSEA taskforce has shared the developments around PSEA at HQ level: All UN agencies to share details of confirmed SEA offenders. A pool of SEA offenders is accessible for UN agencies for reference checks during hiring process. accessible for UN agencies for reference checks during hiring process.
| 5. Conduct PSEA capacity Mapping of HCT members/Map out available resources and materials on prevention and response and practices (referral servicies, capacities of agencies, etc) | X |  |  |  | 0 |  | Taskforce Coordinator |  |  | Q1: Mapping exercise on agency specific was done via online survey targeting all HCT agencies. 13 HCT members responded, establishing a benchmark on existing practices , capacities and gaps as regards PSEA, to guide moving forward with the PSEA
| 6. Conduct High Level discussion at Steering Committee/HCT level on accountability mechanisms for PSEA - Quarterly |  | X | X | X | 0 |  | Taskforce Coordinator |  |  | Q2: 1st Steering committee meeting held in April 2019. Q3: 2nd Steering committee meeting held on Aug 6. Q4: Presentation made to UNCT on the 2020 plans and budget overview
| 7. Develop Standard Operationg Procedures guiding PSEA work in Somalia (To include SEA cases referral process and information sharing) | X | [5 empty] | Taskforce Members |  |  | Q1: Drafted in consultation with the PSEA focal points and with input from HCT members. To be endorsed by the steering committee/HCT Q2: Discussed during the PSEA Steering committee and endorsed. It was renamed from SOP to PSEA Guidance Notes for HCT Somalia. Endorsed, few signatures remaining
| 8. Develop TORs for PSEA focal points | X | [5 empty] | Taskforce Members |  |  | Q1: Drafted in consultation with the PSEA focal points and with input from HCT members. To be endorsed by the steering committee/HCT Q2: Discussed during the PSEA Steering committee and endorsed. It is an annex in the endorsed PSEA Guidance Notes for HCT Somalia.
| 9. Develop Annual PSEA Taskforce work plan | X | [5 empty] | Taskforce Members |  |  | Q1: Drafted in consultation with the PSEA focal points and with input from HCT members. To be endorsed by the steering committee/HCT Q2: Discussed during the PSEA Steering committee and endorsed in April.
| 7. Develop a budget for PSEA activities including CBCM and source for PSEA funding |  | X | X |  |  |  | Co-chairs |  |  | Q1: The budget column to be populated at the next TF meeting scheduled for April 24 Q2: The costed work plan endorsed. Different agencies supporting activities by human and financial resources. IOM has some budget for CBCM training as part of the process of establishment of CBCMs
2. SEA Prevention | 1. Conduct Risk Assessment for SEA in the selected fields/ locations. |  | X | X |  | 10000 | UNICEF | UNICEF/ Taskforce coordinator/Conduct and Discipline |  |  | Q1: UNICEF to include PSEA specific questions in the safety audit. Conduct and Discipline working group (UNSOS/UNSOM) have a working group on risk assessment. Task force coordinator to join in the next meeting. There is need to contact a consultant to carry out a comprehensive SEA risk assessment. Q2: The conduct and discipline working group drafted a Misconduct Risk assessment, that has been shared with the legal department. The draft focuses on internal risks (UNSOS/UNSOM staff) and SEA is part of it. Taskforce coordinator and UNICEF held discussions on various options for understanding the SEA risks especially in the field locations. Options include having specific questions included in the safety audit tool or engaging a consultant to conduct a comprehensive SEA risk assessment. TOR for consultancy was drafted and UNICEF will support the consultancy Q3: Risk assessment contracting of consultants, initial planning meetings, developning the methodology done. Data collection to be don ein 2020.
| 2. Develop Basic information/ IEC materials and key messages on Accountability to Affected Population (AAP) and PSEA to be communicated regularly to beneficiaries, Aid workers and UN personnel. |  | X | X |  | 0 |  | Taskforce Members |  |  | Q2: A small working group was formed to develop the common messaging. UNFPA to engage their office in Nairobi later for assistance in graphic designs. UNHCR to support part of production of the IEC materials Q3: An initial meeting with communication working group took place on Thursday 26 September and………This will be informed by the communication strategy
| 3. Print PSEA IEC materials (Targetting aid workers and communities) |  | X | X | X | 2000 |  | Taskforce Members |  |  | Q2: Some materials to be translated in local language once developed. Q3: Have identified the contacts for translators without borders for possible engagement.
| 4. Conduct ongoing and annual PSEA campaigns through community outreach and public information measures – at national and field level |  |  | X | X | 45000 |  | ??? |  |  | Better to identify 3 implementing Partners to run the PSEA awareness creation and CBCM monitoring. ($15,000 each) Q3: determined that this will not be achieved in 2019 but will be carried on to the 2020 workplan
3. Capacity Building | 1. Hold an orientation workshop for PSEA Focal Points to define the goals and plans for the Taskforce | X |  |  |  | 3500 |  | Taskforce Coordinator and Co-chairs | UNICEF funded the workshop |  | • 3 days’ workshop held (19-21 Feb). Facilitators were Miriam and Yuko. • Cost of the workshop fully covered by UNICEF • PSEA SOPs, PSEA FP TOR, drafted. Individual agencies and inter-agency TF work plans discussed- To be finalized in March) • PSEA capacity assessment, PSEA Compliance self-audit conducted
| 2. Conduct PSEA training for NGOs | X | X | X | X | 17000 |  | Taskforce Cordinator, FPs | IOM ($17,000 available) 3 days CBCM, Baidoa Sept 2019;For TOT, Mapping of Ips with HCT/NGO Consortium Mapping on |  | • Ongoing - PSEA Orientation session held for implementing partners organised by Health sub-cluster (Mogadishu), GBV sub-cluster(Mogadishu) and CP sub-cluster in Hargeisa . • UNICEF organised for a day training to the IPs in CP sub-cluster and is following up on action plans developed. Next training planned for Garowe in April/May 2019 • IOM has secured $17,000 from Australian government to build national NGOs capacity on PSEA and conduct a TOT. Q2: PSEA TOT targeting implementing partners planned for the next Q. IOM secured funding for two training; Orientation sessions and trainings to IPs on PSEA incorporated in the clusters’ capacity building plans, with Education and Child protection clusters planning underway for July Q3: Call for applications went out for PSEA ToT to be carried out in Q4
| 3. Assess what training packages exist globally and develop /make available a PSEA training package for staff (Internal and CBCM) |  | X | X | X | 0 |  | Taskforce Cordinator, FPs | IOM package exit, Discuss the content of the training; |  | Q2: IOM has a training package for training of IPs on PSEA. It is currently under review and the HQ is happy to share with the Somalia taskforce
| 4. Hold a half day session with HCT to understand their roles and PSEA initiative in Somalia | X | X | X |  | 1500 |  | Co-chairs |  |  | Q1. Was conducted in September 2018 and renewed the HCT members commitment. There has been a turnover and therefore a need for another session. Q2. HCT workshop planned for the November 4
| 5.Conduct a ToT for staff from selected NGOs |  | X | X |  | 3500 |  | IOM &Taskforce Coordinator | IOM ($17,00 available)- Aug 2019, potentially with Alex |  | Q1: IOM has secured funding from Australian government for this training. Awaiting signed agreement Q2: IOM received the cash. TOT planned for the next Q. Planning of the TOT ongoing Q3: Call for applications went out for PSEA ToT to be carried out in Q4 Q4 TOT held in November.
4. Mechanism to report and respond to SEA | 1. Activate a common email address for referral of SEA cases to Taskforce coordinator and design a common complaint intake form. |  | X |  |  | 0 |  | Taskforce coordinator, & members |  |  | Q2: Email address created, PSEA.SO@ONE.UN.ORG, Complaints intake form drafted, circulated to members for comments
| 2. Develop a common criteria for selection of the pilot locations for CBCMs |  | X |  |  | 0 |  | Taskforce coordinator,Co-chairs |  |  | Criteria for selection of sites developed.
| 3. Identify the pilot locations ( Identify entry points, develop concept note/mobilize resources collectively) |  | X | X |  | 0 |  | Taskforce Members |  |  | Q1: The next TF meeting (24)will identify the pilot site. Q2: Taskforce members with guidance with the criteria developed agreed to pilot PSEA CBCM in Baidoa
| 4. Hold training on CBCM in identified locations |  |  | X |  | 30000 |  | Taskforce coordinator,Co-chairs |  |  | Q1. First training on CBCM conducted to the TF members in Mogadishu Q2: CBCM training planned for Baidoa in the next Q (Sept) Q3: Coordinator to travel on a mission to Baidoa the week of 13 October to do preliminary work before establishing CBCM- Get buy in, identify representation of various actors, hold orientation sessions on PSEA Q4 Initial buy in steps and identification of stakeholders, mapping of existing CFMs done. The establishment of CBCM to be done in 2020
| 5. Establish community-based complaint & referral mechanisms within all UN entities and partners (including common hotline and common email for reporting SEA, complaint intake form and improved face-to-face reporting). |  |  | X | X |  |  | Taskforce Members |  |  | Q1. Criteria for selection of sites developed. The next TF meeting will identify the pilot site. Zero budget available Q2. Initial process of establishing CBCM pilot in Baidoa in place. Mapping of actors and existing feedback mechanisms ongoing. Complaints form drafted, email set up. Training on CBCM and community consultations to follow
| 6. Develop site specific PSEA CBCM Standard Operating Procedures |  |  | X | X |  |  | Taskfroce Coordinator, & Members
| 7. Establish a PSEA data base |  | X | X | X |  |  | Taskforce Coordinator |  |  | Matrix has been developed. No incident reported so far
| 8. Facilitate referral of SEA survivors to appropriate agencies |  | X | X | X | 0 |  | All agencies | Baidoa done. |  | Q1: To confirm with GBV subcluster the existing referal pathways and services available in various locations Q2: GBV referral pathways updated and circulated in Baidoa. To update other locations in the coming months Q3: Updated GBV referral pathways in Kismaiyo and Banadir
| 9. Follow up on investigation of reported SEA cases |  | X | X | X | 0 |  | All agencies |  |  | No incident has been reported yet
5. Advocacy and communication | 1. Map out NGOs who are not members of HCT and plan for meeting to discuss to be part of the PSEA accountability mechanism |  | X | X |  | 0 |  | Taskforce Coor, co-chairs & NGO Consortium | Related to TOT; List of NGO consurtium membership; |  | Q1: Taskforce Coordinator to reach out to the NGO consortium for the list of members as well as OCHA Q2: Planned PSEA TOT to target NGOs, majority who are not members of HCT. TOT training held in Q4.
| 2. Provide periodic advocacy and quarterly briefs to Steering Committee/HCT and Conduct and Discipline Multi-Disciplinary Working Group(CDMDWG ) on PSEA. |  | X | X | X | 0 |  | Taskforce Coordinator & co-chairs |  |  | Ongoing: HCT Updates: Q1 done in April; Q2 Aug 6; Q3 PSEA was discussed in UNCT; Q4 A presentation was made to UNCT on the progress and the tentative budget for 2020. : CDMDWG : Taskforce is represented in all the quarterly meetings
| 3. Develop a communication strategy- How do we make the work of the taskforce visible? Engagement platform (liaise wit UNDP on this) |  |  | X |  | 0 |  | All agencies |  |  | Q2: The taskforce coordinator tasked to check what already exists at global and country level. Q3: A meeting with communication working group took place on Thursday and……… Q4: Drafted, to be finalized and endorsed by HCT in 2020 communication strategy
| 4. Develop a generic media response on SEA incidents |  | X | X | X | 0 |  | All agencies | Check with community of practice- PSEA coordinators |  | Q2: The taskforce coordinator tasked to check what already exists at global and country level. Q3: A meeting with communication working group took place on Thursday and……… Q4: Included in the drafted to be finalized and endorsed by HCT in 2020 communication strategy
6. Monitoring and Reporting | 1. Produce quarterly and annual report on PSEA in Somalia to HQ |  | X | X | X | 0 |  | Taskforce coordinator & co-chairs |  |  | Q1 Updates presented to the steering committee on April 16, 2019. Q2: Updates to be presented to the steering committee on Aug 6, 2019; Q3 in October
| 2. Track and support implementation of agency-specific PSEA work-plans |  | X | X | X | 0 |  | Taskforce coordinator | To get progress from other agencies |  | Q1: All agencies to share PSEA work plans. Received from WHO, OCHA, UNFPA, CARE, DRC, UNHCR, IOM and ACTED Q2-Q4: Updates from individual agencies shared during the monthly taskforce meetings. So far IOM, ACTED (June), OCHA, UNICEF, UNFPA (July), Worldbank, UNHCR, UNICEF(August), DRC (Nov)