## 2020 Work Plan to endorse
Completed | Inter-agency(UNCT-HCT) taskforce Work Plan - Prevention of Sexual Exploitation and Abuse (PSEA)- Somalia 2020
Ongoing
Not started yet
Thematic Area | Activities | Timeline |  |  |  | Budget | Source of funds | Lead agency | Other agencies | Progress | Comment
|  | Q1 | Q2 | Q3 | Q4
1.Coordination and Engagement | 1. Maintain updated PSEA focal Person list (National level) | X | X | X | X | 0 |  | Co-chairs
| 2. Appoint field level FPs and alternates in Baidoa |  | X | X | X | 0 |  | Steering Committee
| 3. Secure funding for the PSEA Taskforce coordinator | X | X | X | X | 208847 | NORCAP covers 6 months- approx $100,000 | Steering Committee
| 4. Conduct monthly meetings of PSEA task force focal points | X | X | X | X | 0 |  | Taskforce Coordinator
| 5. Conduct regular teleconference with global PSEA Taskforce for advice, sharing of practices and lessons. | X | X | X | X | 0 |  | Co- chairs & Taskforce Coordinator
| 6. Conduct PSEA self-compliance audit to monitor progress over past year and inform internal work plans | X | X |  |  | 0 |  | Taskforce Coordinator and agency members of TF
| 7. Conduct quarterly High Level discussions at Steering Committee/HCT level on accountability mechanisms for PSEA | X | X | X | X | 0 |  | Taskforce Coordinator
| 8. Develop Annual PSEA Taskforce work plan | X |  |  |  | 0 |  | Taskforce
| 9. Develop a budget for PSEA activities | X |  |  |  | 0 |  | Taskforce
| 10. Endorse 2020 workplan | X |  |  |  | 0 |  | Steering committee
2. SEA Prevention | 1. Conduct ongoing and annual PSEA campaigns targeting communities through community outreach and public information measures – at national and field level | X | X | X | X | 30000 |  | Taskforce
| 2. Train Somali radio presenters on PSEA |  |  |  |  | 11576 |  | Taskforce
3. Capacity Building | 1. Refresher workshop/training with Taskforce members at National and Baidoa level |  | X |  | X | 4000 |  | Taskforce coordinator and Co-chairs
| 2. Conduct PSEA training for NGOs | X | X | X | X | 0 |  | Taskforce
| 3. Conduct 2 ToT for selected NGOs - Baidoa and Mogadishu |  | X | X |  | 0 |  | Taskforce
| 4. Create a one folder/one drive on PSEA | X |  |  |  | 0 |  | Taskforce Coordinator
4. Mechanism to report and respond to SEA | 1. Develop a CBCM concept note | X | X |  |  | 0
| 2. Hold training on CBCM in Baidoa |  | X |  |  | 0 |  | Taskforce coordinator and co-chairs
| 3. Establish functional community-based complaint Mechanisms in Baidoa including SOPs |  | X | X | X | 50000 | IOM commits approx $10,000 from Australian govt | Taskforce
| 4. Implement and monitor Baidoa CBCM |  |  | X | X | 0 |  | CBCM Taskforce
| 5. Keep an updated SEA allegations data base |  | X | X | X | 0 |  | Taskforce Coordinator
| 6. Coordinate with GBV Sub-cluster to have up-to-date GBV referal mechanisms |  | X | X |  | 0 |  | TF Coordinator & GBV cluster coordinator
| 7. Facilitate referral of SEA survivors to appropriate agencies | X | X | X | X | 0 |  | All agencies
| 8. Peer accountability- Follow up on response of reported SEA cases | X | X | X | X | 0 | Taskforce Coordinator | All agencies
| 9. Facilitate referral of SEA survivors to appropriate agencies | X | X | X | X | 0 |  | All agencies
| 10. Identify the other locations for CBCM establishment |  |  |  | X | 0 |  | Taskforce
5. Advocacy and communication | 1. Map out and engage NON HCT members- UNCT, NGOs on PSEA to be part of the PSEA accountability mechanism |  | X | X | X | 0 |  | Taskforce Coor, co-chairs & NGO Consortium
| 2. Finalize and endorse communication strategy |  | X |  |  | 0 |  | Taskforce cordinator and Steering committee
0
6. Monitoring and Reporting | 1. Produce quarterly updates and annual report on PSEA in Somalia |  | X | X | X | 0 |  | Taskforce coordinator & co-chairs
| 2. Track and support implementation of agency-specific PSEA work-plans | X | X | X | X | 0 |  | Taskforce coordinator
| 3. Conduct an assessment of the PSEA efforts -2018-2020 |  |  |  | X | 0 |  | Taskforce coordinator
304423
[6 empty] | -104423 | Available funds
[6 empty] | 200000 | Deficit
Note on B17: WARUI Miriam: Have small funding to broadcast PSEA info through talks, adverts, etc after the training- Action plansafter the training- tap into the funding for the campaigns activities above.
Note on B18: WARUI Miriam: W1. Roles of FPs to newly nominated FPs; To look at the progress internally, challenges, share lessons and plan for 2020 W2. Evaluate the progress of 2020 WP and annual report Baidoa Level- The Members roles and on PSEA @2000 per training?? 2 for each level