## PSEA TF
2018 Prevention of Sexual Violence and Abuse (PSEA) Task Force Workplan
Objective: The Tanzania Refugee Interagency Taskforce (PSEA TF) seeks to ensure protection from SEA in the refugee response. It seeks to ensure full commitment of its members to strengthen and enhance the protection and care of all persons of concern, and especially women and children, in situations of humanitarian crisis and establish commitment to the Inter Agency Standing Committee (IASC) Six Core Principles relating to Sexual Exploitation and Abuse. The PSEA TF comprises Focal Points nominated from each agency and organization working in the response who are committed to delivering a workplan to ensure full adherence to the agreed PSEA Protocol.
KEY AREAS OF WORK |  | ACTIVITIES | EXPECTED OUTPUTS | Q1 | Q2 | Q3 | Q4 | COMMENTS | STATUS
PSEA TaskForce Workplan | Coordination and management | Each organisation and agency working in the refugee response to nominate a Focal Point. | When there is turnover, the PSEA Focal Point and HoAs must nominate a new Focal Point. |  | x |  |  | Heads of Agencies | Ongoing. All agencies to provide updates on any changes in FP/Alternates
|  | Attend PSEA Task Force meetings regularly | All Focal Points must attend regular meetings. |  | x | x | x | Focal Points | Taskforce Established
|  | Engage with other relevant networks on PSEA | Focal Points continue to share learning, expertise and best practices. |  | x | x | x | Focal Points | Discussed in SGBV SWG November 2018
|  | Update and share contact lists of PSEA Focal Persons | Updated contact list available. |  | x | x | x | Focal Points | ongoing
|  | Review and update TORs for Task Force | Update and review yearly. | x |  |  |  | Focal Points | ongoing
|  | Develop and agree the Inter Agency Protocol for PSEA | Finalise with HoAs an Inter Agency PSEA Protocol and reach endorsement. |  | x |  |  | Focal Points | Protocol endorsed October
|  | Regional Coordination meeting on PSEA network and CoC Session in Kigoma | HOA and PSEA focal points participate and ensure endormsement of the protocal and 2018 workplan |  | x |  |  | PSEA | Completed October
|  | Training of all PSEA focal points | All focal points are trained on PSEA. |  |  | x |  | PSEA Network | April
| Engagement with and support of beneficaries | Development of culturally appropriate IEC material to be shared with community in different formats. | Specific materials for use in community awareness raising are developed, tested and translated for use in activities. |  | x | x | x | Focal Points/ Community Based Protection Team | May
|  | Develop and roll out IEC dissemintation plan at community level including how to complain. Should be linked to the Community Based Complaints Mechanism communication plan. | Establishment of Inter Agency complaint boxes across the camps ,SOPs developed and operationalised, Sensitisation and awareness on the use of complaint boxes conducted |  |  | x | x | Focal Points/ Community Based Protection Team | April
|  | Develop guidance for the Communicating with Communities (CwC) volunteers and conduct appropriate training. | CwC volunteers are trained and have tailored messages to deliver to the community. |  | x | x | x | Focal Points/ Community Based Protection Team | March
|  | Beneficiary reporting on PSEA complaints | Maintain proper records on documented incidents |  | x | x | x | PSEA Focal Points | Ongoing
| Reporting mechanism | Approriate completion of the IA PSEA referral form | Share the IA referral form within 48 hours |  | x | x | x | PSEA Focal Points | Ongoing
|  | Quaterly reports to the PSEA Networks and Heads of Agencies | Share the quaterly reportshours |  |  |  | x | PSEA Focal Points | To be shared on 5th of the month for each preceeding quarterly period
|  | Ensure prompt referral of reported incidents to competent authorities | Timely referral of the incidents to competent authorities |  | x | x | x | PSEA Focal Points | Ongoing
|  | PSEA focal point to share PSEA quaterly over view report with the Representative | To share the Quaterly report |  | x | x | x | PSEA Focal Points | For period of October-December 2018 to be shared by 5 January 2019
|  | Staff members are periodically informed on ways to file and procedures for handling complaints | Ensure staff are informed on the filing and procedures for handling complaints |  | x | x | x | Admin/ HR/ PSEA Focal Points | To be done systematically in 2019 as part of CoC
| Prevention | Training of trainers (ToT) for Focal Points on PSEA | Completed training for all FPs on PSEA. |  | x |  |  | PSEA Focal Points | Ongoing
|  | Roll out of training at all levels staff, incentive and affiliate workforce | Completed training for all staff members, incentive and affiliate workforce on roles and responsibilities. |  |  | x |  | PSEA Focal Points | Ongoing
|  | Learning event for Senior Managers on PSEA | Completed training for Senior Managers on PSEA. |  | x |  |  | Senior Managers | June
|  | Training of UNHCR/ Partner staff on PSEA | Completed training for UNHCR and partner staff on PSEA |  | x |  |  | PSEA Focal Points | May
|  | Awareness raising and sensitisation of beneficaries on PSEA/ ways of filing complaints and procedures for handling complaints | Completed training for beneficiaries on PSEA/ filing complaints and procedures for handling complaints |  | x | x | x | PSEA Focal Points/ Community Based Protection Team | April
|  | Administration to ensure UNHCR/ Partner, incentive workers and affliated workforce sign a CoC before being offered a contract | All UNHCR/ partner/ incentive workers and affliated workforce sign CoC |  | x | x | x | UNHCR/ Partner/ Affliate Workforce Admin Focal Points | Ongoing
| Developing response mechanisms | Ensure updated PSEA/ SGBV referral pathways are available to all Focal Points. | Circulate updated pathways to all Focal Points. |  | x | x | x | PSEA Focal Points | October
|  | Ensure all incidents are captured in GBVIMS | GBVIMS should track and record all SEA incidents |  | x | x | x | PSEA/ SGBV Focal Points | Ongoing
|  | Provide basic SGBV training for all Focal Points. | Completed training for all Focal Points. |  | x | x | x | SGBV Focal Point/ SGBV Lead Partner | April